## Sheet1
Software bug report
Project name: | Insurance Project
Bug ID | Title/Summary | Issue type | Classification | Environment | Step-by-step | Expected result | Actual result | Link | Attachment | Frequency | Status | Severity | Priority | Source | Notes/Comments | Reporter | Assignee | Reported on | Due date | Date closed | Time logged | Resolution
Bug_001 | Calculated data is incorrect when Parking Location = Public Place | Bug | UI/Usability | Windows 11 - Opera | 1.Navigate to https://demo.guru99.com/insurance 2.Enter Email & Password 3.Click Submit 4.Click Request a quotation 5.Change the Parking Location 6.Click Calculate Premium | The cost increases by £30 compared to not choosing a parking location | Value does not change |  | @ [type @ to add] | Always | In progress | Critical | High | Internal | [Additional notes or comments regarding the issue] | Tuấn | @ | 18/7/2024 | @ | @ | 17:00 | [Describe how the issue was resolved for future reference]
Bug_003 | Profile is not saved | Bug | UI/Usability | Windows 11 - Opera | 1.Navigate to https://demo.guru99.com/insurance 2.Enter Email & Password 3.Click Submit 4.Click Edit Profile 5.Fill in the information according to the form 6.Click Submit 7.Click Profile | Displays previously submitted information | Profile is not saved |  |  | Always | In progress | Critical | High | Internal |  | Tuấn |  | 18/7/2024 |  |  | 17:00
Bug_006 | Do not proceed when Estimated value = 100 even though the conditions are met | Bug | UI/Usability | Windows 11 - Opera | 1.Navigate to https://demo.guru99.com/insurance 2.Enter Email & Password 3.Click Submit 4.Click Request a quotation 5.Change Estimated value 6.Click Calculate Premium | Calculate the Premium value | Do not proceed |  |  | Always | In progress | Severity | High | Internal |  | Tuấn |  | 18/7/2024 |  |  | 17:00
Bug_007 | The insurance premium calculation function in insurance is calculated incorrectly | Bug | UI/Usability | Windows 11 - Opera | 1.Navigate to https://demo.guru99.com/insurance 2.Enter Email & Password 3.Click Submit 4.Click Request a quotation 5.Change Total Mileage 6.Click Calculate Premium | Cost increased by £50 compared to total mileage <= 5000 | Value does not change |  |  | Always | Done | Severity | High | Internal |  | Tuấn |  | 18/7/2024 |  |  | 17:00
Bug_008 | Currently Your Discount is: 30% even though there is no discount | Bug | UI/Usability | Windows 11 - Opera | 1.Navigate to https://demo.guru99.com/insurance 2.Enter Email & Password 3.Click Submit 4.Click Request a quotation | Show 0% discount | Show Your Discount is: 30% |  |  | Always | To do | Severity | High | Internal |  | Tuấn |  | 18/7/2024 |  |  | 17:00
Manage your to-do task lists with Plaky.com
Issue type |  |  | Classification | [5 empty] | Status |  |  | Severity
Bug | 5 |  | Security | 0 |  |  |  |  | To do | 1 |  | Minor | 0
Suggestion | 0 |  | Performance | 0 |  |  |  |  | In progress | 2 |  | Medium | 0
New feature | 0 |  | UI/Usability | 5 |  |  |  |  | In review | 0 |  | Major | 0
|  |  | Syntax | 0 |  |  |  |  | Done | 1 |  | Critical | 2
|  |  | Crash | 0 |  |  |  |  | Discarded | 0